## WBS
WBS # | Task Description | Task Lead | Est Duration | Start Date
1 | 1st Generation Saturn - Thermal Characterization | Robert
1.1 | Calibration Data Reduction
1.2 | Thermal Profile Development
1.3 | Test Plan Development
1.4 | Test Execution
1.5 | Test Data Reduction
1.6 | Documentation of Test Results
2 | Calibration Script Rewrite | April
2.1 | Existing Cal Process Intro
2.2 | Cal Script Handoff
2.3 | Saturn A3 Chassis Retrofit
2.4 | Testbed Setup
2.5 | New Calibration Script Development
3 | Passive Front End Modeling | Tiffany | Jason
3.1 | QUCS S-Parameter Ideal Model Development
3.2 | Monte Carlo Simulation of Gen 1 Passive Front End
3.3 | Passive Front End Model White Paper Development
4 | Passive Front End H/W Model Construction | Cody
4.1 | Schematic Capture
4.2 | Board Layout
4.3 | PCB Spin
4.4 | Stuff PCB
4.5 | Characterize (VNA)
4.6 | Passive Front End H/W Model White Paper
5 | Passive Front End H/W Model - Thermal Characterization | Robert
5.1 | Test Execution
5.2 | Test Data Reduction
5.3 | Passive Front End H/W Model Thermal Char. White Paper
6 | Passive Front End Redesign | Tiffany | Jason
6.1 | Balun Selection
6.2 | Matching Network Design
6.3 | Modification of QUCS Simulation
6.4 | Passive Front End Redesign - White Paper
7 | Final Presentation Development | All

## Deliverables
Deliverable ID | Title | Description | Due Date
1 | Gen 1 Saturn Thermal Test Plan |  | 2016-01-04
2 | Next Generation Calibration Script |  | 2016-01-13
3 | Passive Front End Model - White Paper |  | 2016-01-20
4 | Passive Front End H/W Model - Design Package |  | 2016-02-13
5 | Passive Front End H/W Model - Thermal Char. - White Paper |  | Floating
6 | Passive Front End Redesign - White Paper |  | Floating
7 | Final Presentation |  | 2017-05-04

## Risk Register
Risk ID
1
2
3
4
5